## Recruitment Goals
Tri Yearly Milestones | 2019 |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023
| 2019-08-01 | 2019-12-01 | 2019-04-01 | 2019-08-01 | 2019-12-01 | 2019-04-01 | 2019-08-01 | 2019-12-01 | 2019-04-01 | 2019-08-01 | 2019-12-01 | 2019-04-01
Original Target: Total Recruitment
Target: Total Recruitment | 3 | 15 | 27 | 43 | 55 | 71 | 83 | 99 | 111 | 127 | 143 | 150
Actual: Total Recruitment | 7 | 26 | 35 | 46 | 56 | 70 | 80 | 98 | 107
Actual/Target Ratio: Total Recruitment | 100%
Status: Total Recruitment | Actual Autopassed
Original Target: Racial Minority Recruitment
Target: Racial Minority Recruitment | 1 | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40 | 45
Actual: Racial Minority Recruitment | 0
Actual/Target Ratio: Racial Minority Recruitment | 0%
Status: Racial Minority Recruitment | Actual Pending Review
Original Target: Hispanic Ethnicity Recruitment
Target: Hispanic Ethnicity Recruitment | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4
Actual: Hispanic Ethnicity Recruitment | 0
Actual/Target Ratio: Hispanic Ethnicity Recruitment | ~
Status: Hispanic Ethnicity Recruitment | Actual Autopassed

## Sheet4
| 2021 | 2022
| December | January | February | March
Follow-ups due by month | 10 | 14 | 13 | 13
Completed | 8 | 11 | 6 | 0
Scheduled | 0 | 0 | 6 | 8
Missed | 2 | 0 | 0 | 0
To be scheduled | 0 | 3 | 1 | 5
|  | 1137 T4 | 1214 T2
1136 t4
1196 t2

## Enrollment by month
2019 | [5 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec | January | February | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
7 | 7 | 4 | 4 | 4 | 6 | 1 | 1 | 1 | 1 | 1 | 4 | 5 | 3 | 2 | 3 | 2 | 1 | 4 | 3 | 6 | 3 | 2 | 2 | 3 | 3 | 6 | 5 | 4 | 3 | 2 | 4

## Timepoint progress
| T1 | T2 | T3 | T4
Complete | 99 | 70 | 58 | 48
Missed | 4 | 9 | 11 | 7